## Sheet1
S.No | Tasks | Working Hours | Tools & Technology | Task status
| Web API BackEnd | Tuesday
1 | DB Design and table creation | 4hrs | MS SQL | Done
2 | Project Report | 2hrs | Excel | Done
Wed/Thur
3 | Stored Procedure | 3hrs | MS SQL
4 | Authentication Login/register | 5hrs | Identity
5 | Web API | 4hrs | Dapper
| Angular Front-End | Friday/Monday
Admin Page design
6 | Toggle nav-bar | 1hr | ngIf,(click)
7 | Common Layout(header,footer..) | 3hr | Angular material & Flex
8 | Search,filter,pagination | 3hrs | Angular material
9 | Add Products - form | 2hrs | Material Forms
10 | Form-Validations | 4hrs | Custom-Directives
11 | Display Products by list | 2hr | Table
12 | hover on img | 2hrs | Angular Material
| User Page design | Tuesday
13 | Products list in Cards | 3hrs | Angular material
14 | display based on category | 3hrs | Angular material
15 | apply pagination,filter,search | 3hrs | Angular material